## Sheet1
Starting Criteria
Week | 7 | Days
Weekly Work | 5 | Days
Weekly Work | 37 | Hours
Prof Dev Module | 0.25 | Proportion of total year effort
Live Project | 0.55 | Proportion of Prof Dev
Effort |  |  |  | Totals |  |  | For Selection |  | For Selection |  | For Selection
Minimum |  |  |  | 5.0875 | Hours per Week |  | Minimum |  | Term |  | Requirements
Expected | 1 | Extra-curricular hours per night |  | 10.0875 | Hours per Week |  | Expected |  | Non-term |  | Design
Stretch | 2 | Extra curricular hours per night |  | 15.0875 | Hours per Week |  | Stretch |  |  |  | Impl
None
| Start Date | Year | Month | Day
|  | 2018 | 10 | 23 | 2018-10-23
|  |  | Investigation | [6 empty] | 564
|  |  | Requirements |  |  | 224 | Design |  |  | 340 | Implementation | [8 empty] | 850 | Release |  |  | 340
Project | Phishing Button For Email (Outlook)
|  |  | Term | Term | Term | Term | Term | Term | Term | Term | Non-term | Non-term | Non-term | Term | Term | Term | Term | Term | Term | Term | Term | Term | Term | Term |  | Hours
| Member | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
|  | Sprint | 1: 0.75; 3: 1.75; 5: 2.75; 7: 3.75; 9: 4.75; 11: 5.75; 13: 6.75; 15: 7.75; 17: 8.75; 19: 9.75; 21: 10.75
|  | Commencing | 2018-10-23 | 2018-10-30 | 2018-11-06 | 2018-11-13 | 2018-11-20 | 2018-11-27 | 2018-12-04 | 2018-12-11 | 2018-12-18 | 2018-12-25 | 2019-01-01 | 2019-01-08 | 2019-01-15 | 2019-01-22 | 2019-01-29 | 2019-02-05 | 2019-02-12 | 2019-02-19 | 2019-02-26 | 2019-03-05 | 2019-03-12 | 2019-03-19 |  | Minimum | Expected | Stretch | Total
| CrunchyNutBatman (Tech Lead) |  | None | Minimum | None | Expected | Minimum | Minimum | Expected | Expected | Minimum | Minimum | Minimum | Minimum | Expected | Minimum | Expected | Expected | Minimum | Stretch | Expected | Expected | Stretch | Stretch |  | 45.7875 | 80.7 | 45.2625 | 171.75
| HoneyLoops (Project Manager) |  | None | None | None | Expected | Minimum | Minimum | Expected | Expected | Minimum | Minimum | Minimum | Minimum | Expected | Minimum | Expected | Expected | Minimum | Stretch | Expected | Expected | Stretch | Stretch |  | 40.7 | 80.7 | 45.2625 | 166.6625
| CheeriosBatman (User Advocate) |  | None | Minimum | None | Expected | Minimum | Minimum | Expected | Expected | Minimum | Minimum | Minimum | Minimum | Expected | Minimum | Expected | Expected | Minimum | Stretch | Expected | Expected | Stretch | Stretch |  | 45.7875 | 80.7 | 45.2625 | 171.75
| Neil Fredrickson (Tech Lead) |  | None | Minimum | None | Expected | Minimum | Minimum | Expected | Expected | Minimum | Minimum | Minimum | Minimum | Expected | Minimum | Expected | Expected | Minimum | Stretch | Expected | Expected | Stretch | Stretch |  | 45.7875 | 80.7 | 45.2625 | 171.75
| TheBlackYellow10 (Client Advocate) |  | None | Minimum | None | Expected | Minimum | Minimum | Expected | Expected | Minimum | Minimum | Minimum | Minimum | Expected | Minimum | Expected | Expected | Minimum | Stretch | Expected | Expected | Stretch | Stretch |  | 45.7875 | 80.7 | 45.2625 | 171.75
| Member 6 |  | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
| Hours | Minimum | 2 | 2 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | Expected | 10 | 10 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | Totals | 223.85 | 403.5 | 226.3125 | 853.6625 | Hours
|  | Stretch | 15 | 15 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
| Total Hours | Week | 27 | 27 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | Total |  |  | 1754 |  | Hours
| Total Hours | Sprint | 2018-10-30: 54; 2018-11-13: 170; 2018-11-27: 170; 2018-12-11: 170; 2018-12-25: 170; 2019-01-08: 170; 2019-01-22: 170; 2019-02-05: 170; 2019-02-19: 170; 2019-03-05: 170; 2019-03-19: 170 | Total |  |  | 1754 |  | Hours
You have | 1754 | Hours, to spend on your project